Silitex × Sapirim — Meeting notes

Teams call · 16/10/2026 · 2 h 07 m
Dr. Federica Biti, Eleonora Pravato (Silitex) · Giorgio Lucchini · Avshi Sapir (Sapirim)

How to use: just click a box ☐ when a task is done, save, and reply with this file attached — or simply reply "done 1, 3". No login, no app needed.

✅ Silitex — your tasks

| Done | # | Task | Owner / due |
| --- | --- | --- | --- |
| ☐ | 1 | IT review of portal + email filtering; send IT questions / protocol. | Silitex IT / Federica |
| ☐ | 2 | Present the Sapirim approach to the owners for approval. | Federica |
| ☐ | 3 | Send list of products to promote (best sellers) + cosmetics counter-type list (Dow, BRB). | Federica / Eleonora |
| ☐ | 4 | Send question list per application for sample requests. | Federica / Eleonora |
| ☐ | 5 | Agree product names for Israel. | Federica / Eleonora |
| ☐ | 6 | Check elastomer-gel equivalent (CXG-1104). | Federica / Eleonora |
| ☐ | 7 | Success stories, if available. | Federica / Eleonora |
| ☐ | 8 | Later: online sector trainings; introduction to owners. | Federica |

✅ Sapirim — our tasks (for your information)

| Done | # | Task | Owner / due |
| --- | --- | --- | --- |
| ☐ | 1 | Send the presentation as PDF (portal blocked). | Avshi |
| ☐ | 2 | Create WhatsApp group (Federica, Eleonora, lab) + send mobile. | Avshi |
| ☐ | 3 | Answer Silitex IT questions; propose whitelist or tools.silitex.it. | Avshi |
| ☐ | 4 | Check whether Israel still allows D5 in cosmetics → answer Federica. | Avshi |
| ☐ | 5 | Send NuSil CSF-3504 / CXG-1104 account details to Federica. | Avshi |
| ☐ | 6 | Propose private product-name scheme (prefix) for Israel. | Avshi |
| ☐ | 7 | Request next meeting when questions/feedback are ready. | Avshi |

What we agreed

Focus first on silicone fluids, personal care / cosmetics and antifoams.

Food sector on hold for now — we revisit in about 6 months.

No country-wide exclusivity at the start: step by step per sector, distinct product names for Israel.

Communication: a WhatsApp group (Federica, Eleonora, lab) + short online technical meetings.

Open questions

Does Israel still allow D5 in cosmetics? (Avshi → Federica)

Is the biggest Israeli detergent producer tied to a licensor silicone supply? (Avshi)

Elastomer-gel equivalent of CXG-1104? (Silitex lab)

Portal / email whitelisting — IT decision and owners approval (Silitex)

Avshi Sapir · Sapirim · +972 50-523-1042 · avshi@sapirim.com